## Sheet1
Module | Task | Assigned | Status | Start Date | Exp End Date | Act End Date | Issues
Hardware for GPS | Selection of Gps Hardware | Girija | Completed | 16/10/2023 | 18/10/2023 | 18/10/2023
| Neo 6m | Girija | Completed | 16/10/2023 | 18/10/2023 | 18/10/2023 | Accuracy is very low
| Neo7m | Sharooq | Completed | 16/10/2023 | 18/10/2023 | 18/10/2023 | Choosing the right microcontroller was challenging. Arduino is not supported. Raspberry pi 3b and zero is supported
| Extracting coordinates from neo7m | Sharooq | Completed | 19/10/2023 | 23/10/2023 | 23/10/2023 | Receiving signals strength is good near corners and open space than within building
| Sim 808 - GPS and GSM | Girija/Sharooq/Gokul | Completed | 29/10/2023 | 2023-01-11 | 2023-02-11 | couldn’t connect the model to any micro controller
| Save the coordinates to csv file with timestamp | Sharooq | Completed | 23/10/2023 | 24/10/2023 | 24/10/2023
Web Page Creation | Creating a Webpage using sockets to display the Realtime coordinates. | Sharooq | Completed | 25/10/2023 | 30/10/2023 | 30/10/2023
| Integrating Coordinates to webpage | Sharooq | Completed | 31/10/2023 | 2023-03-11 | 2023-03-11
GeoFencing | Build realtime geofencing(code) | Sharooq | Completed | 2023-06-11 | 17/11/2023 | 16/11/2023
| Integrate with webpage | Sharooq | Completed | 17/11/2023 | 23/11/2023 | 24/11/2023
Layout Pinpointing | Extract Layout from Google map and converting to image | Sharooq | Completed | 27/11/2023 | 2023-04-11 | 2023-07-12
| Extract corner points in image | Sharooq | Completed | 2023-08-12 | 2023-11-12 | 2023-11-12
| Pixel conversion | Sharooq | Completed | 2023-11-12 | 19/12/2023 | 19/12/2023
| Live coordinates marking | Sharooq | Completed | 19/12/2023 | 22/12/2023 | 20/12/2023
| Multiple live coordinates | Sharooq | Completed | 20/12/2023 | 22/12/2023 | 21/12/2023
Tkinter application | Creating tkinter application for GPS tracking | Sharooq | Completed | 21/12/2023 | 28/12/2023 | 26/12/2023
| Configurable coordinates from file | Sharooq | Completed | 21/12/2023 | 28/12/2023 | 26/12/2023
| Implementing Live Tracking, History Tracking | Sharooq | Completed | 21/12/2023 | 28/12/2023 | 26/12/2023
| Demo with multiple coordinates with live and history tracking | Sharooq | Completed | 21/12/2023 | 28/12/2023 | 26/12/2023
| Custom Layout Marking in Live tracking | Sharooq | Completed | 27/12/2023 | 2024-03-01 | 2024-03-01
| Marking points in custom Layout | Sharooq | Completed | 2024-04-01 | 2024-09-01 | 2024-09-01
| Adding ids, color and png to each vehicles | Sharooq | Completed | 2024-09-01 | 2024-11-01 | 2024-10-01
| Bay marking, counting and displaying the number of vehicles in each bay | Sharooq | Completed | 2024-10-01 | 2024-12-01 | 2024-12-01
| Filter Selection of Vehicle | Sharooq | Completed | 16/1/2024 | 18/1/2024 | 18/1/2024
| Creating different layouts for different plants | Sharooq | Completed | 19/1/2024 | 23/1/2024 | 23/1/2024
| Live tracking of multiple vehicles - plantwise | Sharooq | Completed | 19/1/2024 | 23/1/2024 | 23/1/2024
| Demo Preparation with History Tracking | Sharooq | Completed | 23/1/2024 | 24/1/2024 | 24/1/2024
| Extracting Coordinates from excel file. | Sharooq | Completed | 25/1/2024 | 29/1/2024 | 29/1/2024
| Using Sockets to transfer data from raspberrypi to system success. | Sharooq | Completed | 29/1/2024 | 31/1/2024 | 30/1/2024
| Exploration of kafka and zookeeper for transferring data from raspberrypi to system | Sharooq | Completed | 30/1/2024 | 2024-01-02 | 2024-02-02 | Kafka didn’t work as memory allocated limit exceeded in raspberrypi due to low RAM. Therefore, Kafka Implementation failed.
| Generating Random coordinates for multiple trucks | Sharooq | Completed | 2024-05-02 | 2024-06-02 | 2024-06-02
| Integrating Random Coordinates to the Source Code | Sharooq | Completed | 2024-06-02 | 2024-06-02 | 2024-06-02
| Implementing Geofencing region which extracted from excel file. | Sharooq | Completed | 2024-06-02 | 2024-07-02 | 2024-07-02
| Updating the truck count in each geofence region in the table dynamically | Sharooq | Completed | 2024-07-02 | 2024-08-02 | 2024-08-02
| Implementing of History Tracking using toggle button | Sharooq | Completed | 2024-08-02 | 2024-08-02 | 2024-08-02